## TDM milestones
TDM MILESTONES | 2024 | [7 empty] | 2025
| MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
TDM Technical Committee Tasks
TDM retreat, participate (completed) | bar: 2024 SEP; 2024 NOV
State CTR Plan: advise and approve (finalizing) | bar: 2024 SEP; 2024 NOV; 2025 APR to 2025 JUL
Statewide TDM workplan 2025 Q3-Q4: advise, approve and support | bar: 2024 SEP; 2024 NOV; 2025 APR to 2025 DEC
Statewide TDM strategic plan: advise, approve, approve and support | bar: 2024 SEP; 2024 NOV; 2025 OCT to 2025 DEC
World Cup TDM pilot sprint team: participate and legislative advocacy (completed) | bar: 2024 SEP; 2024 NOV; 2025 JAN to 2025 APR
World Cup TDM pilot sprint team next steps: participate | bar: 2024 SEP; 2024 NOV; 2025 APR
Mobility Partnerships Grant, legislative advocacy (paused) | bar: 2024 OCT to 2025 DEC
Mobility Partnerships Grant (or new TDM programming and funding): planning, engagement | bar: 2024 OCT to 2025 DEC
CTR plans (local and regional): review and approve | bar: 2024 SEP; 2024 NOV to 2025 JUN
CTR 2025-2029 funding formula: advise and approve | bar: 2025 JAN to 2025 MAY
CTR-affected cities: advise and approve | bar: 2025 JAN to 2025 DEC
CTR Tax Credit: engage legislators and legislative staff (paused) | bar: 2024 OCT to 2025 APR
CTR plans (local and regional): qualitive review of engagement requirement | bar: 2024 OCT to 2024 DEC; 2025 MAR to 2025 JUN
CTR Report to the Legislature: advise | bar: 2025 JUN to 2025 DEC
CTR Implementers' Tasks
CTR program implementation in alignment with administrative workplan
CTR plans (local and regional), develop, conduct engagement, draft (Completed) | bar: 2024 MAY to 2024 OCT; 2025 JAN to 2025 APR
CTR surveys, conduct | bar: 2024 MAY to 2024 JUN; 2024 OCT to 2024 NOV; 2025 MAR to 2025 JUN
CTR program reports, conduct | bar: 2024 OCT to 2025 JUN
CTR tax credit, promote to employers | bar: 2024 OCT to 2025 JUN
CTR plans (local and regional), submit to state for review (completed) | bar: 2024 NOV to 2025 MAR
CTR plans (local and regional), obtain local approval (completed) | bar: 2025 JAN to 2025 JUN